## Cover
IOS+ Implementation Budget
Lamar University — Education Compliance Platform
Total Year 1 Investment |  | $520,000 | Implementation + Phase 1
5-Year TCO |  | $760,000 | Including annual recurring
Est. 5-Year Value |  | $2,500,000–$4,000,000 | ROI 3.3x–5.3x
Break-Even |  | Month 8–14 | After Phase 1 go-live
Workbook Contents
Summary | High-level implementation budget by phase and use case
Phase Detail | Line-item breakdown of development, infrastructure, and integration costs
Annual Recurring | Ongoing operational costs: infrastructure, support, maintenance
Staffing Plan | FTE requirements and role responsibilities by phase
ROI & Value | Return on investment: quantified value by use case
Timeline | Phased 18-month implementation roadmap with milestones

## Summary
IOS+ Implementation Budget Summary
Phased investment by use case — Lamar University
Phase | Use Case | Dev Cost | Infra Cost | Integration | Total Phase | Annual Value
Phase 1 | UC-00: AI Governance + Core Engine | 180000 | 35000 | 50000 | 265000 | 0
Phase 2 | UC-01: Predictive Persistence | 70000 | 10000 | 0 | 80000 | 150000
Phase 3 | UC-02: Transcript Evaluation | 55000 | 5000 | 0 | 60000 | 50000
Phase 4 | UC-03/04: Accreditation + Alignment | 45000 | 5000 | 0 | 50000 | 100000
Phase 5 | UC-05/06: Grading Load + Allied Health | 35000 | 5000 | 0 | 40000 | 200000
TOTALS
Note: Annual Value estimates are conservative. UC-01 attrition reduction alone (5–10% first-year retention) generates $150K–$300K/year in retained tuition revenue.

## Phase Detail
Line-Item Budget Detail
Development, infrastructure, and integration costs by category
Phase 1 — Core Engine + AI Governance (Months 1–6)
Category | Line Item | Qty | Rate | Subtotal | Vendor/Notes
Development | Node.js middleware engine (Gate 530 + orchestration) | 1 | 120000 | 120000 | Contractor + internal team
Development | COS+ PostgreSQL database layer (WORM + audit) | 1 | 40000 | 40000 | Contractor + DBA
Development | Evidence fabric (Ed25519 signing + JCS) | 1 | 20000 | 20000 | Contractor
Infrastructure | PostgreSQL server (on-premise) | 1 | 25000 | 25000 | Dell/HP server hardware
Infrastructure | pgvector extension + setup | 1 | 5000 | 5000 | Open source, labor only
Infrastructure | Network security (firewall, VPN) | 1 | 5000 | 5000 | Existing IT
Integration | Banner/Ellucian Ethos API connector | 1 | 35000 | 35000 | Ellucian partner
Integration | Blackboard REST API connector | 1 | 25000 | 25000 | Blackboard partner
Integration | Concourse API connector | 1 | 15000 | 15000 | Concourse partner
Integration | SSO / identity federation (SAML) | 1 | 10000 | 10000 | Existing IT + contractor
Phase 1 Total
Phase 2 — Predictive Persistence (Months 7–9)
Category | Line Item | Qty | Rate | Subtotal | Vendor/Notes
Development | Risk scoring engine (Banner + Blackboard signals) | 1 | 45000 | 45000 | Contractor
Development | Advisor intervention queue dashboard | 1 | 25000 | 25000 | Contractor
Infrastructure | Additional compute for batch processing | 1 | 10000 | 10000 | Server upgrade
Phase 3 — Transcript Evaluation (Months 10–12)
Category | Line Item | Qty | Rate | Subtotal | Vendor/Notes
Development | Catalog matching engine (course equivalency) | 1 | 35000 | 35000 | Contractor
Development | Visual confidence bands + approval workflow | 1 | 20000 | 20000 | Contractor
Infrastructure | Document storage upgrade (transcript scans) | 1 | 5000 | 5000 | Storage array
Phase 4 — Accreditation + Outcome Alignment (Months 13–15)
Category | Line Item | Qty | Rate | Subtotal | Vendor/Notes
Development | SACSCOC standards mapping engine | 1 | 25000 | 25000 | Contractor
Development | Readiness Heat Map dashboard | 1 | 20000 | 20000 | Contractor
Development | CLO ↔ Blackboard assessment drift detector | 1 | 15000 | 15000 | Contractor
Infrastructure | Document indexing (414 existing files) | 1 | 5000 | 5000 | Labor only
Phase 5 — Grading Load + Allied Health Reporting (Months 16–18)
Category | Line Item | Qty | Rate | Subtotal | Vendor/Notes
Development | Grading Load Index calculator | 1 | 20000 | 20000 | Contractor
Development | Allied health programmatic dashboard | 1 | 15000 | 15000 | Contractor
Infrastructure | Additional reporting compute | 1 | 5000 | 5000 | Server upgrade

## Annual Recurring
Annual Recurring Costs
Ongoing operational costs starting Year 2 (after implementation)
Cost Category | Year 2 | Year 3–5 | Notes
Infrastructure (server, storage, network) | 25000 | 25000 | On-premise hardware maintenance
PostgreSQL maintenance + backups | 8000 | 8000 | DBA time + backup storage
Security patching + monitoring | 6000 | 6000 | IT security staff time
Application support (bug fixes, minor enhancements) | 25000 | 25000 | Contractor retainer or 0.5 FTE
Training & documentation updates | 10000 | 10000 | Annual faculty/staff training
Ellucian Ethos API maintenance | 5000 | 5000 | Annual license/support
Blackboard API maintenance | 3000 | 3000 | Annual license/support
Concourse API maintenance | 2000 | 2000 | Annual license/support
Annual Recurring Total
Note: Year 1 includes all implementation costs plus prorated annual recurring. Total Year 1 = $495,000 (implementation) + $42,000 (prorated recurring) = $537,000.

## Staffing Plan
Staffing Plan by Phase
FTE requirements and role responsibilities
Role | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Total (FTE-months)
Project Manager | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 15
Backend Engineer (Node.js/TypeScript) | 1.5 | 0.75 | 0.75 | 0.5 | 0.5 | 24
Database Administrator (PostgreSQL) | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 7.5
Frontend Engineer (React/Vue) | 0.75 | 0.5 | 0.5 | 0.5 | 0.5 | 13.5
DevOps / Infrastructure Engineer | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 7.5
Compliance / Data Governance Officer | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 7.5
Banner/Ellucian Integration Specialist | 0.5 | 0 | 0 | 0 | 0 | 3
Blackboard Integration Specialist | 0.5 | 0 | 0 | 0 | 0 | 3
QA / Testing Engineer | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 7.5

## ROI & Value
Return on Investment Analysis
Conservative value estimates by use case
Use Case | Value Driver | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
UC-01: Predictive Persistence | Retained tuition (5–10% attrition reduction) | 150000 | 175000 | 200000 | 225000 | 250000
| Advisory time savings (automated queue) | 20000 | 25000 | 30000 | 35000 | 40000
UC-02: Transcript Evaluation | Faster yield + staff time savings | 40000 | 50000 | 60000 | 70000 | 80000
UC-03: Accreditation | Avoided crisis / emergency remediation | 200000 | 50000 | 50000 | 50000 | 50000
UC-04: Outcome Alignment | SACSCOC compliance assurance | 30000 | 40000 | 50000 | 60000 | 70000
UC-05: Grading Load | Rational support allocation | 15000 | 20000 | 25000 | 30000 | 35000
UC-06: Allied Health | NCLEX-RN threshold protection | 500000 | 100000 | 100000 | 100000 | 100000
UC-00: AI Governance | FERPA violation avoidance | 50000 | 50000 | 50000 | 50000 | 50000
TOTAL ANNUAL VALUE
5-Year Total Value (conservative): $2,500,000 — $4,000,000 ¦ 5-Year TCO: $760,000 ¦ Net ROI: 3.3x–5.3x

## Timeline
Implementation Timeline
18-month phased roadmap with key milestones
Phase | Timeline | Deliverable | Go-Live | Budget | Faculty Impact
Phase 1 | Months 1–6 | Core engine + AI governance | Month 6 | 265000 | FERPA compliance enforced; all tools audited
Phase 2 | Months 7–9 | Predictive persistence + advisor queue | Month 9 | 80000 | Early warning alerts for at-risk students
Phase 3 | Months 10–12 | Transcript evaluation workflow | Month 12 | 60000 | 2-day transcript turnaround
Phase 4 | Months 13–15 | Accreditation heat map + drift detection | Month 15 | 50000 | Continuous SACSCOC readiness
Phase 5 | Months 16–18 | Grading load + allied health dashboard | Month 18 | 40000 | Programmatic compliance tracking
Key Milestones: Month 3 = Banner/Blackboard integration complete ¦ Month 6 = Gate 530 live ¦ Month 9 = First advisor intervention queue ¦ Month 12 = Transcript eval live ¦ Month 15 = SACSCOC readiness dashboard ¦ Month 18 = Full platform operational